## Untitled
Defect ID | Defect Description | Severity | Priority | Status | Assigned To | Resolution
1 | Patient search function in EHR module returns incorrect results for certain search criteria | High | High | In Progress | John Smith | Investigating the root cause of the issue. Will update with findings by [date].
2 | Appointment scheduling fails when booking appointments outside of regular clinic hours | Medium | Medium | Open | Jane Doe